{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["WBS"],"not_rendered":{"macros":1,"comments":1},"read":"whole","date_system":"1900"}

{"sheet":"WBS","index":0,"n_rows":18,"n_cols":10,"rows_kept":18,"merged":[[0,0,0,16383]]}
[]
["WBS Number","Task Name","WBS Description","Must Start by Date","Must End by Date","Task Level of Effort\n(in hours)","Task Duration\n(in days)","Predecessor\n(Finish-to-Start Dependency)\n(comma separated)","Resource Name(s)","Author\n(of Item for follow-on questions)"]
["1","Develop the Shopping Cart","The Shopping Cart will need to be developed for the Web Site.  This effort requires development of a database structure and loading the product data. "]
["1.1","Develop the Database Structure"]
["1.2","Load Data into the Database"]
["1.2.1","Build the Product Catalog"]
["1.2.1.1","Identify Products"]
["1.2.1.2","Contact Vendors","request quotes from 3 Vendors, provide vendors with specifications","12/28/2015","01/15/2016",10,5,"1.2.1.1","Jeremy Buyers ","Name of PM or assistant PM"]
["1.2.1.3","Submit Agreements"]
["2","Purchase the Infrastructure"]
["2.1","Purchase Hardware"]
["2.2","Purchase Software"]
["3","Develop the Web Site"]
["3.1","l2"]
["3.2","Design the Interface"]
["3.3","Build the Web Interface"]
["3.4","Test the Web Interface",{"$nulls":5},3.2]
["3.5","Deploy the Web Interface"]